## Using this template
Template communications plan for the Cancer Quality of Life Survey
What is the Cancer Quality of Life Survey? NHS England and Public Health England are leading the way in cancer care by recognising that quality of life (QoL) outcomes are as important to patients as survival. We are launching a nationwide QoL survey in breast, prostate and colorectal cancer patients in September 2020. We expect that the survey will include all cancer types from 2021 onwards. Everyone diagnosed with cancer will be a sent a survey 18-months after their diagnosis to assess their quality of life. The information collected from the survey will be used to work out how best to support people living with and beyond cancer. This is an ambitious programme with a scale and depth that isn’t being matched anywhere else in the world.
What are Cancer Alliances being asked to do? Cancer Alliances have been asked to produce a communications planning, setting out how they plan to raise awareness of the Cancer Quality of Life Survey in their local areas. We need to ensure that NHS staff know about the survey so that they can encourage people to complete the survey, respond to queries about the survey and support patients to access additional support. To support Alliances, we have produced this template commmunications plan to help focus your communications work and provide some examples of activities that you could deliver. You are not required to use this template and you can adapt it or add to it, to suit your needs.
How to use this template This template should help you to: • be clear about what you are trying to achieve with your communications so that you can appropriately focus your activity and resources • map and prioritise your stakeholders • plan communications acitivities using the channels that your stakeholders already use and trust • log the communications activities you have delivered and record any feedback or insight for the national team. Once complete, this template can be shared within and across teams to ensure a common understanding of priorities.
Other resources We have also created a communications toolkit with a range of products to help you promote the survey. The toolkit can be found on the Cancer Alliance Workspace. https://future.nhs.uk/canc/view?objectID=19564592 The national survey fieldwork supplier, Quality Health, will also be hosting a website www.CancerQoL.england.nhs.uk and helpline 0800 783 1775 to support people to complete the survey.

## Objectives
Communications objectives
All of your communications activities should look to achieve one or more of the following objectives: 1. Promote uptake of the survey in patients by: • Encouraging patients to complete the survey. • Increasing awareness of the survey to make it recognisable and trustworthy to patients. • Ensuring NHS staff are equipped to respond to general queries from patients and know where to direct them for further support to complete the survey. 2. Promote awareness of the survey in trusts and primary care by: • Ensuring NHS staff know about the survey and how the findings will be used. • Asking NHS staff to share the key messages more widely with anyone involved in delivery of care to people affected by cancer. 3. Assess the ‘readiness to change' locally and foster support for the survey by: • Engaging with stakeholders to understand the current approach to QoL locally. • Encouraging a shift towards recognising that quality of life is as important to patients as survival. • Generating interest in the findings of the survey and how they can be used to drive improvements in care.

## Stakeholder mapping
Stakeholder Mapping
It is important to have a clear view of who you are trying to communicate with and why, and you should tailor your approach to their particular needs, interests and challenges. Investing time at the outset of your plan should help bring focus to your communications approach. The interest–ability matrix in this section can help you prioritise your stakeholders. Place your identified stakeholders on the matrix below in response to the following questions: 1. What level of interest does this stakeholder have, or potentially have, in the QoL survey? 2. What level of ability does this stakeholder have in helping us achieve our communications objectives?
High influence | Active engagement - Satisfy | Key players - Manage | Stakeholders that sit in the top right quadrant have high levels of interest in the QoL survey and they are in a good position to help you achieve your objectives. Strategically, these are going to be the most relevant Stakeholders to target your communications at. Stakeholders that sit in the top left quadrant have low levels of interest in what you are trying to achieve but potentially high influence on, or ability to achieve, your objectives. Stakeholders in this quadrant may be important but will be harder to reach and require more communications resources to engage than those in the top right quadrant.
Low influence | Monitor | Keep informed | Stakeholders that sit in the bottom right quadrant have an interest in the QoL survey but have little direct influence on, or ability to achieve, your objectives. In communications terms it might be appropriate to keep these stakeholders aware or broadly informed about the survey but not concentrate resources on them. Stakeholders that sit in the bottom left quadrant have low levels of interest in the QoL survey and low levels of ability to achieve or influence your objectives. In most instances, you can take these out of your communications plans.
| Low interest | High interest

## Channels
Existing channels
In this section, you should think about the existing channels used to communicate with each of the stakeholders that you have listed in your mapping exercise (particularly, those to be managed, monitored and satisfied). You should also consider if any additional targeted comms is needed e.g. a separate email or briefing, organising a call or meeting. You can then refer to this section when planning comms activities to ensure that you have made the best use of all existing channels and opportunities to engage.
Stakeholder | Existing channels | Additional opportunities
NHS (commissioner)
NHS (provider)
Local Authorities
Charity and voluntary sector
Information and support groups

## Planned comms activities
Planned communications and engagement activities
Activity | When | Stakeholder(s) | Objective | Relevant part(s) of toolkit | Complete?
What comms activities do you have planned? What channel(s) will you use? E.g. meetings, updates, newsletters, bulletins, website, social media, direct email, briefing. Refer to the 'channels' section to ensure you haven't missed anything. | When will the planned activity take place? | Who are you trying to reach? E.g. patients, NHS staff, primary care, local charities. You could reach multiple stakeholders with a particular communication. Refer back to your stakeholder mapping to ensure that you have communications planned for all key stakeholders. | It can help to align all communicactions activites to one or more of the objectives below: 1.Promote uptake of the survey in patients 2. Promote awareness of the survey in trusts and primary care 3. Understand the current approach to QoL locally; assess ‘readiness to change' 4. Support patients and respond to queries | Consider if any of the materials we have produced to support your communications would be useful: • Visual identity guide • Tailored slide set(s) • Slide template • Briefing notes and key messages • Locally printable poster • Social media suggestions • FAQs • Example surveys and letters • QoL Case Studies • Survey website - www.CancerQoL.england.nhs.uk | To keep track of what has been delivered, mark activities as either planned, ongoing or complete.
Post on social media to notify followers that the QoL survey is launching in September and to direct them to further information: - Tweet from Cancer Alliance Twitter - Monitor any replies - Encourage colleagues to tweet from their personal accounts - Retweet the National Cancer Programme | September 2020 | All | 1. Promote uptake of the survey in patients 2. Promote awareness of the survey in Trusts and Primary Care | Social media suggestions
Add an agenda item to discuss the QoL survey at key meetings | August-December 2020 | Add audience for specific meeting here | Add objective(s) here depending on stakeholders targeted | Key messages Slideset or slide template Journey map QoL case studies FAQs
Ensure the Cancer Alliance website and individual Trust websites are updated to include information about the QoL survey and a link to the public-facing website. | August 2020 | All | 1. Promote uptake of the survey in patients 2. Promote awareness of the survey in Trusts and Primary Care | Key messages Survey website
Print copies of the QoL survey poster and ensure they are displayed in areas that are visible to patients and to healthcare professionals involved in delivery of care to people affected by cancer. Share the poster with contacts in Primary Care to ensure it is displayed in GP practices and pharmacies. | August 2020 | Patients, public, healthcare professionals in Trusts and in Primary Care | 1. Promote uptake of the survey in patients 2. Promote awareness of the survey in Trusts and Primary Care | Locally printable poster
Include an update about the QoL survey in various bulletins, updates or newsletters | August-December 2020 | Add audience for specific meeting here | Add objective(s) here depending on stakeholders targeted | Key messages
Contact local charities by email, letting them know that the survey is launching and directing them to more info via the survey website | September 2020 | Local charities (list here) | 1. Promote uptake of the survey in patients 3. Assess the ‘readiness to change' locally and foster support for the survey | Key messages
Present to local Patient Advisory Board about the survey or include an update on the agenda for their next meeting. | August-December 2020 | Patients | 1. Promote uptake of the survey in patients | Key messages Slideset or slide template
Actively engage with local Healthwatches to ensure the QoL survey is understood and any requests for more information or findings are noted | September 2020 | Local Healthwatch, patients, public | 3. Assess the ‘readiness to change' locally and foster support for the survey | Key messages

## Feedback & evaluation
Feedback and evaluation
You should use this section to evaluate the effectiveness of the communications activities that you have delivered. You should record the number of stakeholders you have reached. For example, you could record: • the number of attendees at a meeting/event • the number of recipients of a bulletin/newsletter • the number of posters printed • the number of likes or retweets on Twitter. Those delivering communications will be also able to gather insight and feedback on how the survey has been received by a range of stakeholders. You should also this section to record any feedback on the QoL survey, both positive and negative, and any questions about the survey or how the data will be used. Notable feedback and insight can be sent to Erin.Barton@nhs.net and shared at monthly networking calls with LWBC leads.
Comms activity | When? | Who? | Feedback?
Note the communications activity that was delivered | Note when the activity took place | Who was at the meeting/who did you contact? Include here any figures you have for the number of people reached e.g. the number of attendees at a meeting, the number of people to receive an email/newsletter, the number of posters printed. | How was the QoL survey received? Did stakeholders have questions/queries? Was there any notable feedback for the national team?